## Checklist
Category | Task | Owner | Status | Deadline | Notes
Enrollment | Consolidate returning students by class | Leadership / Front office | To do | 2026-08-20
Enrollment | Review incomplete files and missing documents | Front office | To do | 2026-08-22
Fees | Validate school fees by level and payment schedules | Leadership / Finance | To do | 2026-08-18
Fees | Test receipts and payment tracking workflow | Finance | To do | 2026-08-23
Classes | Validate student assignment by class | Academic leadership | To do | 2026-08-24
Classes | Check room capacity and overload risks | Discipline office | To do | 2026-08-24
Timetables | Publish a first operational timetable version | Academic leadership | To do | 2026-08-26
Team | Assign critical reopening responsibilities | Leadership | To do | 2026-08-21
Team | Brief office and finance teams on the reopening workflow | Leadership | To do | 2026-08-25
Parents | Send reopening information to parents | Front office | To do | 2026-08-27
Parents | Share required documents and schedules | Front office | To do | 2026-08-27
Academics | Review subjects coefficients and teacher assignments | Academic leadership | To do | 2026-08-25
Academics | Prepare the grade-entry framework | Academic leadership | To do | 2026-08-28
Student life | Check attendance absence and discipline tracking | Discipline office | To do | 2026-08-28
Offline | Prepare a fallback procedure for unstable internet | Leadership / IT | To do | 2026-08-28
Day one | Verify class lists welcome flow and contact points | Leadership | To do | 2026-08-31